## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2171-swen-261-04-b Grade A Slackers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | KP; 10/17
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | KP; 10/17
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | KP; 10/17
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | KP; 10/17
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | KP; 10/17
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | KP; 10/17
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | KP; 10/17
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | KP; 10/17
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | KP; 10/17
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | KP; 10/17
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | KP; 10/17
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | KP; 10/17
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | KP; 10/17
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | KP; 10/17
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | KP; 10/17
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | KP; 10/17
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | KP; 10/17
As a game I want to validate a player's frontward movement so that the move coincides with the rules of checkers. | Given that it is my turn when I drag a piece to a space behind my piece, then the piece should not be droppable.
Given that is is my turn when I drag a piece to an adjacent black space in front of my piece then the piece should be droppable.
Given that it is my turn when I drag a piece to a white space, then I expect the piece to not be droppable.
Given that it is my turn when I drag a piece to an occupied space, then the piece should not be droppable.
Given that it is my turn when I drag a piece to a space that should not be reachable in one move, then the piece should not be droppable.
Given that it is my turn when I try to drag one of my opponents pieces, then the piece should be unmovable.
As a Player I want to be able to move my pieces so that I can move the game along. | Given that it is not my turn when I try to move a piece, then I should not be able to drop the piece.
Given that I have moved a piece, when I click the submit move button, then I expect my turn to be over.
Given that I have not moved a piece when I click the submit move button, then I expect the system to not allow me to end my turn.
Given that I have moved a piece when it was my turn, then I expect my move to be reflected across both mine and my opponent's screens.
As a Player I want to Capture Opponent Pieces so that I can get closer to winning. | Given that one of my pieces has jumped over an opponent's piece on my turn, when I click submit move, then I expect the piece to be removed from the board.
Given that one of my pieces has jumped over one or more of my opponent's pieces, when I click submit move, then I expect all jumped-over pieces to be removed.
Given that I have a piece capable of jumping an opponent's piece on my turn and I do not take it, when I submit my turn, then I should get an error message telling me I have to capture the opponent's piece.
Given a turn that has one or more jumps available, when I submit a turn that contains any one of those jumps, then the turn should be considered valid.
Given that I have a jump available, when I submit a turn without making a jump, then the turn should be considered invalid.
As a player, I want to disconnect from a game, so that I may be able to play more games. | Given that I am in a game when I choose to resign, then I expect to be taken back to the home page.
Given that I am on the home page when I have resigned from my precious game, then I expect to be able to start a new game with another player.
Given that I am in a game when my opponent resigns, then I expect to be taken back to the home page with a message that lets me know that player has resigned.
Given that I am in a game when I click the sign-out link at the top, then I expect to be taken back to the home page and shown the number of users in the lobby but not their names.
Given that I am in a game when my opponent signs-out, then I expect to be taken back to the home page and remain signed in, with a message telling me that the other player has signed out.
Given that I am about to resign when I click the resign button then I should see a message asking me if I want to resign.