## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2171-swen-261-04-b Grade A Slackers
Testing Team Name | Grade B Slackers Reese Jones and Nick Mancini

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Freshman Seminar | Tester initials; date; comments (required if test failed) | Team C | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | We see two means of signing in, we are wondering why you made this desicion
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected, again we are not sure why there are two, but both seem to work.
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Fail | Works as expected for most cases, but in the case where one player has the name of a single space, and the second player has the name of two spaces, the game is not made.
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Fail | It is droppable, which is a good thing.
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | KP; 10/17 |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a game I want to validate a player's frontward movement so that the move coincides with the rules of checkers. | Given that it is my turn when I drag a piece to a space behind my piece, then the piece should not be droppable. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that is is my turn when I drag a piece to an adjacent black space in front of my piece then the piece should be droppable. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn when I drag a piece to a white space, then I expect the piece to not be droppable. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn when I drag a piece to an occupied space, then the piece should not be droppable. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn when I try to drag one of my opponents pieces, then the piece should be unmovable. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a Player I want to be able to move my pieces so that I can move the game along. | Given that I have moved a piece, when I click the submit turn button, then I expect my turn to be over. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn when when I move a piece and click submit turn, then I expect my move to be reflected across both mine and my opponent's screens. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn and I have moved a piece when I press the backup button, then I expect to have that piece return to its start state. |  |  |  |  | Pass | NM:11/16/17 | Fail | Jumps are not undone properly, when you back up a jump, it does not add the jumped piece back to the board. Then another move can be made, but the piece will still be gone.
| Given that it is my turn and I have not made a move when I click the submit turn button, then I expect to have the system not allow me to end my turn. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is not my turn when my opponent submits their move, then I expect it to be my turn. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a player, I want to disconnect from a game, so that I may be able to play more games. | Given that it's my turn and I haven't moved yet when I choose to resign, then I expect to be taken back to the home page. | [6 empty] | Pass | Works as expected.
| Given that I am on the home page when I have resigned from my previous game, then I expect to be able to start a new game with another player. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I am in a game when my opponent resigns, then I expect to be taken back to the home page with a message that lets me know that player has resigned. |  |  |  |  | Fail | RJ:11/16/17:Player did return to home screen but only after the game board page was refreshed | Pass | Works as expected.
| Given that it is not my turn when I choose to resign then I expect to be taken back to the home page. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn and I have made a move but not submitted my turn, when I choose to resign then I expect the system to not allow me to resign. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a Game I want to check if a jump was legal so that my move doesn't violate the rules of the transcendent game of checkers. | Given that it is my turn, when I have jumped over a piece and the piece I moved has another jump available, then I expect my turn to continue. |  |  |  |  | Pass | NM:11/16/17 | Pass | A lot of weird stuff happens with jump and back up, but in general it works. Back up can crash the server.
| Given that it is my turn and I have not moved my piece when a jump is present, then I expect the system to stop me from making any move other than said jump. |  |  |  |  | Pass | NM:11/16/17 | Pass | In general, works as expected.
| Given that it is my turn and I have not moved a piece when two separate jumps are present, then I expect the system to restrict me to only making one of the two jumps. |  |  |  |  | Pass | NM:11/16/17 | Pass | In general, works as expected.
As a Game I want to validate a players backwards movement so that the move coincides with the rules of checkers. | Given that it is my turn when I move a king piece then I expect the system to let me be able to move the backwards. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn when there is a valid jump available behind a king piece, then I expect the system to allow me to make said jump. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my turn when I move a single piece backwards then I expect to be denied the ability to make that move |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a Player I want to Capture Opponent Pieces so that I can get closer to winning. | Given that one of my pieces has jumped over an opponent's piece on my turn, when I click submit move, then I expect the piece to be removed from the board. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that one of my pieces has jumped over one or more of my opponent's pieces, when I click submit move, then I expect all jumped-over pieces to be removed. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I have a piece capable of jumping an opponent's piece on my turn and I do not take it, when I submit my turn, then I should get an error message telling me I have to capture the opponent's piece. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given a turn that has one or more jumps available, when I submit a turn that contains any one of those jumps, then the turn should be considered valid. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that I have a jump available, when I submit a turn without making a jump, then the turn should be considered invalid. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a Player I want to upgrade a normal piece to a king so that I have a stronger piece than can help me win. | Given that it is my turn when I move a single piece to the last row of my opponents side of the board then I expect the system to turn my single piece into a king. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that it is my opponents turn when they move their piece to the last row of my end of the board then I expect to see that piece change to a king. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
| Given that my single piece has been upgraded to a king when I reach the opposite end of the board then I excpect my piece to be able to move backwards. |  |  |  |  | Pass | NM:11/16/17 | Pass | Works as expected.
As a Player I want the game to check if I or my opponent has won after each of our moves so that the game does not go on indefinitely. | Given my opponent has lost all of their pieces when my turn is over then I expect the system to alert me that I have won and end the game.
Given my opponent cannot move when I corner their remaining pieces then I expect the system to alert me that I have won and end the game.
Given a user has won a checkers match when the user has made a winning move then the user should be redirected back to the homescreen with a message saying that the user has won.
Given that my opponent has captured my last piece when it is their turn then I expect the system to alert me that I have lost and end the game.
Given that it is my opponents turn when all of my pieces are cornered then I expect the system to alert me that I have lost and end the game.
As a user I want to see a clickable list of my past games so that I can rewatch them. | Given I am on the home page when I have not played any games then I should see an empty list of games.
Given I have finished a game when I am on the home page then I expect to see that game in my list of played games.
Given I have not selected a game when I click the replay button then I expect to see a message telling me to choose a game to replay.
Given I have selected a game when I click the replay button then I expect to be taken to the game screen.
Given I am on the replaying board when I do nothing then I expect the game to replay automatically.
Given I am on the replaying board when I try to move a piece then I expect nothing to happen.
Given I am on the replaying board when the game is some replaying then I expect to be taken back to the home.
As a player I want to have a spectator mode available so that I may view other players' games. | Given that I am signed in, when I am on the home page then I expect to see a list of games in progress.
Given that I am signed in, when I click on a current game, then I expect to be able to enter the game as a spectator.
Given that I am playing a game, when a player joins as a spectator then I expect to be able to continue playing my game as before.
Given that I am signed in, when I choose to spectate a game then I expect to be removed from the list of current players.
Given that I am a spectator when I am viewing a game then I expect to have no permissions